## Gantt Chart
BIOEN/EE 461/561 GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | MyoGrind: A Wearable EMG Device for Bruxism |  |  |  |  | CLASS NAME | [6 empty] | Neural Technology Studio
PROJECT MEMBERS |  | Emily Rodgers, Elijah McReeb, Aditya Krishna, Frenda Lin, Poojitha Arangam |  |  |  |  | DATE | [6 empty] | 2024-04-14
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 2 (4/1 - 4/5) |  |  |  |  | WEEK 3 (4/8 - 4/12) |  |  |  |  | WEEK 4 (4/15 - 4/19) |  |  |  |  | WEEK 5 (4/22 - 4/26) |  |  |  |  | WEEK 6 (4/29 - 5/3) |  |  |  |  | WEEK 7 (5/6 - 5/10) |  |  |  |  | WEEK 8 (5/13 - 5/17) |  |  |  |  | WEEK 9 (5/20 - 5/24) |  |  |  |  | WEEK 10 (5/27 - 5/31) |  |  |  |  | WEEK 11 6/3 - 6/7) |  |  |  |  | WEEK 12 (6/10 - End)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Surveying Skills and Project Fit | Emily | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.2 | Submit Final Project Decision | ALL | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.3 | Design Gallery Walk Poster | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.4 | Develop Project Timeline | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.5 | Assign Roles and Responsibilities | Frenda | 2024-04-15 | 2024-04-17 | 2 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
2 | Market Analysis
2.1 | Shortlist 5 Interview Candidates | ALL | 2024-04-15 | 2024-04-16 | 1 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 4 (4/15 - 4/19) T
2.2 | Design Interview Script/Questions | Frenda | 2024-04-15 | 2024-04-17 | 2 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 4 (4/15 - 4/19) W
2.3 | Interview Candidates | ALL | 2024-04-17 | 2024-04-23 | 6 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 5 (4/22 - 4/26) T
2.4 | Interview Response Analysis | Emily | 2024-04-19 | 2024-04-22 | 3 | 0% | bar: WEEK 4 (4/15 - 4/19) F to WEEK 5 (4/22 - 4/26) M
3 | Prototype Development
3.1 | Preliminary Hardware System | Elijah | 2024-04-22 | 2024-05-03 | 11 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 6 (4/29 - 5/3) F
3.2 | EMG Detection Software | Aditya | 2024-04-22 | 2024-05-06 | 14 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 7 (5/6 - 5/10) M
3.3 | Preliminiary User Control App | Poojitha | 2024-04-29 | 2024-05-06 | 7 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) M
3.4 | Hardware + Software Integration | Aditya/Elijah | 2024-04-29 | 2024-05-10 | 11 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) F
3.5 | Midterm Presentation Preparation | Emily/Frenda | 2024-04-29 | 2024-05-10 | 11 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) F
3.6 | EDN Notebook Responsibilities | Emily/Frenda | 2024-04-22 | 2024-05-10 | 18 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 7 (5/6 - 5/10) F
4 | Compliance and Testing
4.1 | Polished Hardware System | Elijah | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.2 | Advanced Analysis / Troubleshooting | Aditya | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.3 | Polished User Interface | Poojitha | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.4 | Testing on users + Designing Demo | Poojitha/Aditya/Elijah | 2024-05-17 | 2024-05-26 | 9 | 0% | bar: WEEK 8 (5/13 - 5/17) F to WEEK 10 (5/27 - 5/31) M
5 | Go-to-Market Stategy
5.1 | Draft Project Report; What More Needs To Be Done? | Frenda/Emily | 2024-05-13 | 2024-05-24 | 11 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 9 (5/20 - 5/24) F; WEEK 11 6/3 - 6/7) R
5.2 | Project Demo Prep | Elijah/Poojitha/Aditya | 2024-05-27 | 2024-06-05 | 8 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R
5.3 | Final Project Presentation Prep | Emily/Frenda | 2024-05-27 | 2024-06-05 | 8 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R
5.4 | Final Project Presentation | ALL | 2024-05-27 | 2024-06-06 | 9 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R

## Poojitha
BIOEN/EE 461/561 GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | MyoGrind: A Wearable EMG Device for Bruxism |  |  |  |  | CLASS NAME | [6 empty] | Neural Technology Studio
PROJECT MEMBERS |  | Emily Rodgers, Elijah McReeb, Aditya Krishna, Frenda Lin, Poojitha Arangam |  |  |  |  | DATE | [6 empty] | 2024-04-14
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 2 (4/1 - 4/5) |  |  |  |  | WEEK 3 (4/8 - 4/12) |  |  |  |  | WEEK 4 (4/15 - 4/19) |  |  |  |  | WEEK 5 (4/22 - 4/26) |  |  |  |  | WEEK 6 (4/29 - 5/3) |  |  |  |  | WEEK 7 (5/6 - 5/10) |  |  |  |  | WEEK 8 (5/13 - 5/17) |  |  |  |  | WEEK 9 (5/20 - 5/24) |  |  |  |  | WEEK 10 (5/27 - 5/31) |  |  |  |  | WEEK 11 6/3 - 6/7) |  |  |  |  | WEEK 12 (6/10 - End)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.2 | Submit Final Project Decision | ALL | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.3 | Design Gallery Walk Poster | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.4 | Develop Project Timeline | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
2 | Market Analysis
2.1 | Shortlist 5 Interview Candidates | ALL | 2024-04-15 | 2024-04-16 | 1 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 4 (4/15 - 4/19) T
2.3 | Interview Candidates | ALL | 2024-04-17 | 2024-04-23 | 6 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 5 (4/22 - 4/26) T
3 | Prototype Development
3.3 | Preliminiary User Control App | Poojitha | 2024-04-29 | 2024-05-06 | 7 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) M
4 | Compliance and Testing
4.3 | Polished User Interface | Poojitha | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.4 | Testing on users + Designing Demo | Poojitha/Aditya/Elijah | 2024-05-17 | 2024-05-26 | 9 | 0% | bar: WEEK 8 (5/13 - 5/17) F to WEEK 10 (5/27 - 5/31) M
5 | Go-to-Market Stategy
5.2 | Project Demo Prep | Elijah/Poojitha/Aditya | 2024-05-27 | 2024-06-05 | 8 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R
5.4 | Final Project Presentation | ALL | 2024-05-27 | 2024-06-06 | 9 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R

## Frenda
BIOEN/EE 461/561 GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | MyoGrind: A Wearable EMG Device for Bruxism |  |  |  |  | CLASS NAME | [6 empty] | Neural Technology Studio
PROJECT MEMBERS |  | Emily Rodgers, Elijah McReeb, Aditya Krishna, Frenda Lin, Poojitha Arangam |  |  |  |  | DATE | [6 empty] | 2024-04-14
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 2 (4/1 - 4/5) |  |  |  |  | WEEK 3 (4/8 - 4/12) |  |  |  |  | WEEK 4 (4/15 - 4/19) |  |  |  |  | WEEK 5 (4/22 - 4/26) |  |  |  |  | WEEK 6 (4/29 - 5/3) |  |  |  |  | WEEK 7 (5/6 - 5/10) |  |  |  |  | WEEK 8 (5/13 - 5/17) |  |  |  |  | WEEK 9 (5/20 - 5/24) |  |  |  |  | WEEK 10 (5/27 - 5/31) |  |  |  |  | WEEK 11 6/3 - 6/7) |  |  |  |  | WEEK 12 (6/10 - End)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Surveying Skills and Project Fit | Emily | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.2 | Submit Final Project Decision | ALL | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.3 | Design Gallery Walk Poster | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.4 | Develop Project Timeline | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.5 | Assign Roles and Responsibilities | Frenda | 2024-04-15 | 2024-04-17 | 2 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
2 | Market Analysis
2.1 | Shortlist 5 Interview Candidates | ALL | 2024-04-15 | 2024-04-16 | 1 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 4 (4/15 - 4/19) T
2.2 | Design Interview Script/Questions | Frenda | 2024-04-15 | 2024-04-17 | 2 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 4 (4/15 - 4/19) W
2.3 | Interview Candidates | ALL | 2024-04-17 | 2024-04-23 | 6 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 5 (4/22 - 4/26) T
2.4 | Interview Response Analysis | Emily | 2024-04-19 | 2024-04-22 | 3 | 0% | bar: WEEK 4 (4/15 - 4/19) F to WEEK 5 (4/22 - 4/26) M
3 | Prototype Development
3.1 | Preliminary Hardware System | Elijah | 2024-04-22 | 2024-05-03 | 11 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 6 (4/29 - 5/3) F
3.2 | EMG Detection Software | Aditya | 2024-04-22 | 2024-05-06 | 14 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 7 (5/6 - 5/10) M
3.3 | Preliminiary User Control App | Poojitha | 2024-04-29 | 2024-05-06 | 7 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) M
3.4 | Hardware + Software Integration | Aditya/Elijah | 2024-04-29 | 2024-05-10 | 11 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) F
3.5 | Midterm Presentation Preparation | Emily/Frenda | 2024-04-29 | 2024-05-10 | 11 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) F
3.6 | EDN Notebook Responsibilities | Emily/Frenda | 2024-04-22 | 2024-05-10 | 18 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 7 (5/6 - 5/10) F
4 | Compliance and Testing
4.1 | Polished Hardware System | Elijah | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.2 | Advanced Analysis / Troubleshooting | Aditya | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.3 | Polished User Interface | Poojitha | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.4 | Testing on users + Designing Demo | Poojitha/Aditya/Elijah | 2024-05-17 | 2024-05-26 | 9 | 0% | bar: WEEK 8 (5/13 - 5/17) F to WEEK 10 (5/27 - 5/31) M
5 | Go-to-Market Stategy
5.1 | Draft Project Report; What More Needs To Be Done? | Frenda/Emily | 2024-05-13 | 2024-05-24 | 11 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 9 (5/20 - 5/24) F; WEEK 11 6/3 - 6/7) R
5.2 | Project Demo Prep | Elijah/Poojitha/Aditya | 2024-05-27 | 2024-06-05 | 8 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R
5.3 | Final Project Presentation Prep | Emily/Frenda | 2024-05-27 | 2024-06-05 | 8 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R
5.4 | Final Project Presentation | ALL | 2024-05-27 | 2024-06-06 | 9 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R

## Aditya
BIOEN/EE 461/561 GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | MyoGrind: A Wearable EMG Device for Bruxism |  |  |  |  | CLASS NAME | [6 empty] | Neural Technology Studio
PROJECT MEMBERS |  | Emily Rodgers, Elijah McReeb, Aditya Krishna, Frenda Lin, Poojitha Arangam |  |  |  |  | DATE | [6 empty] | 2024-04-14
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 2 (4/1 - 4/5) |  |  |  |  | WEEK 3 (4/8 - 4/12) |  |  |  |  | WEEK 4 (4/15 - 4/19) |  |  |  |  | WEEK 5 (4/22 - 4/26) |  |  |  |  | WEEK 6 (4/29 - 5/3) |  |  |  |  | WEEK 7 (5/6 - 5/10) |  |  |  |  | WEEK 8 (5/13 - 5/17) |  |  |  |  | WEEK 9 (5/20 - 5/24) |  |  |  |  | WEEK 10 (5/27 - 5/31) |  |  |  |  | WEEK 11 6/3 - 6/7) |  |  |  |  | WEEK 12 (6/10 - End)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.2 | Submit Final Project Decision | ALL | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.3 | Design Gallery Walk Poster | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.4 | Develop Project Timeline | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
2 | Market Analysis
2.1 | Shortlist 5 Interview Candidates | ALL | 2024-04-15 | 2024-04-16 | 1 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 4 (4/15 - 4/19) T
2.3 | Interview Candidates | ALL | 2024-04-17 | 2024-04-23 | 6 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 5 (4/22 - 4/26) T
3 | Prototype Development
3.2 | EMG Detection Software | Aditya | 2024-04-22 | 2024-05-06 | 14 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 7 (5/6 - 5/10) M
3.4 | Hardware + Software Integration | Aditya/Elijah | 2024-04-29 | 2024-05-10 | 11 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) F
4 | Compliance and Testing
4.2 | Advanced Analysis / Troubleshooting | Aditya | 2024-05-12 | 2024-05-16 | 4 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 8 (5/13 - 5/17) F
4.4 | Testing on users + Designing Demo | Poojitha/Aditya/Elijah | 2024-05-17 | 2024-05-26 | 9 | 0% | bar: WEEK 8 (5/13 - 5/17) F to WEEK 10 (5/27 - 5/31) M
5 | Go-to-Market Stategy
5.2 | Project Demo Prep | Elijah/Poojitha/Aditya | 2024-05-27 | 2024-06-05 | 8 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R
5.4 | Final Project Presentation | ALL | 2024-05-27 | 2024-06-06 | 9 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R

## Elijah
BIOEN/EE 461/561 GANTT CHART | [5 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE | [5 empty] | CLASS NAME | [6 empty] | Neural Technology Studio
PROJECT MEMBERS | [5 empty] | DATE | [6 empty] | 2024-04-14
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 2 (4/1 - 4/5) |  |  |  |  | WEEK 3 (4/8 - 4/12) |  |  |  |  | WEEK 4 (4/15 - 4/19) |  |  |  |  | WEEK 5 (4/22 - 4/26) |  |  |  |  | WEEK 6 (4/29 - 5/3) |  |  |  |  | WEEK 7 (5/6 - 5/10) |  |  |  |  | WEEK 8 (5/13 - 5/17) |  |  |  |  | WEEK 9 (5/20 - 5/24) |  |  |  |  | WEEK 10 (5/27 - 5/31) |  |  |  |  | WEEK 11 6/3 - 6/7) |  |  |  |  | WEEK 12 (6/10 - End)
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Surveying Skills and Project Fit | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.2 | Submit Final Project Decision | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.3 | Design Gallery Walk Poster | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.4 | Develop Project Timeline | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.5 | Assign Roles and Responsibilities | 2024-04-15 | 2024-04-17 | 2 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
2 | Market Analysis
2.1 | Shortlist 5 Interview Candidates | 2024-04-15 | 2024-04-16 | 1 | 0% | WEEK 4 (4/15 - 4/19) W: At least 2 Interview Candidates Contributed
2.2 | Design Interview Script/Questions | 2024-04-15 | 2024-04-17 | 2 | 0% | WEEK 4 (4/15 - 4/19) R: 2 Main Interview Questions Contributed
2.3 | Interview Candidates | 2024-04-17 | 2024-04-23 | 6 | 0% | WEEK 5 (4/22 - 4/26) W: Conducted at least 1 Interview, helped with more
3 | Prototype Development
3.1 | Preliminary Hardware System | 2024-04-22 | 2024-05-03 | 11 | 0% | WEEK 5 (4/22 - 4/26) F: EMG ability to be detected and sent to computer; WEEK 7 (5/6 - 5/10) M: Hardware System allows EMG detection and vibration feedback
3.2 | EMG Detection Software | 2024-04-22 | 2024-05-06 | 14 | 0% | WEEK 5 (4/22 - 4/26) F: Threshold algorithm for easy detection of an event; WEEK 7 (5/6 - 5/10) T: Assisting Aditya with signal processing for bruxism detection
3.3 | Hardware + Software Integration | 2024-04-29 | 2024-05-10 | 11 | 0% | WEEK 5 (4/22 - 4/26) W: ^prelim EMG recorded for early testing; WEEK 8 (5/13 - 5/17) M: Hardware able to detect bruxism and provide response
3.4 | Midterm Presentation Preparation | 2024-04-29 | 2024-05-10 | 11 | 0% | WEEK 8 (5/13 - 5/17) M: Demonstration or Slides for mideterm presentation
3.5 | EDN Notebook Responsibilities | 2024-04-22 | 2024-05-10 | 18 | 0% | WEEK 8 (5/13 - 5/17) M: Assistance with writeups
4 | Compliance and Testing
4.1 | Polished Hardware System | 2024-05-12 | 2024-05-16 | 4 | 0% | WEEK 9 (5/20 - 5/24) M: Hardware fits in one device, likely still wired, fits on head
4.2 | Advanced Analysis / Troubleshooting | 2024-05-12 | 2024-05-16 | 4 | 0% | WEEK 9 (5/20 - 5/24) M: Assisting Aditya with group decided improvements
4.3 | Testing on users + Designing Demo | 2024-05-17 | 2024-05-26 | 9 | 0% | WEEK 10 (5/27 - 5/31) T: Two videos of users using device, tweaks if they give feedback
5 | Go-to-Market Stategy
5.2 | Project Demo Prep | 2024-05-27 | 2024-06-05 | 8 | 0% | WEEK 11 6/3 - 6/7) F: Two videos of demo, rehearsed live demo for class
5.3 | Final Project Presentation Prep | 2024-05-27 | 2024-06-05 | 8 | 0% | WEEK 11 6/3 - 6/7) F: Slides complete and rehearsed
5.4 | Final Project Presentation | 2024-05-27 | 2024-06-06 | 9 | 0% | WEEK 11 6/3 - 6/7) F: Slides complete and presented

## Emily
BIOEN/EE 461/561 GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | MyoGrind: A Wearable EMG Device for Bruxism |  |  |  |  | CLASS NAME | [6 empty] | Neural Technology Studio
PROJECT MEMBERS |  | Emily Rodgers |  |  |  |  | DATE | [6 empty] | 2024-04-15
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 2 (4/1 - 4/5) |  |  |  |  | WEEK 3 (4/8 - 4/12) |  |  |  |  | WEEK 4 (4/15 - 4/19) |  |  |  |  | WEEK 5 (4/22 - 4/26) |  |  |  |  | WEEK 6 (4/29 - 5/3) |  |  |  |  | WEEK 7 (5/6 - 5/10) |  |  |  |  | WEEK 8 (5/13 - 5/17) |  |  |  |  | WEEK 9 (5/20 - 5/24) |  |  |  |  | WEEK 10 (5/27 - 5/31) |  |  |  |  | WEEK 11 6/3 - 6/7) |  |  |  |  | WEEK 12 (6/10 - End)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Surveying Skills and Project Fit | Emily | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.2 | Submit Final Project Decision | ALL | 2024-04-01 | 2024-04-08 | 7 | 100% | bar: WEEK 2 (4/1 - 4/5) M to WEEK 3 (4/8 - 4/12) M
1.3 | Design Gallery Walk Poster | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
1.4 | Develop Project Timeline | ALL | 2024-04-08 | 2024-04-15 | 7 | 100% | bar: WEEK 3 (4/8 - 4/12) M to WEEK 4 (4/15 - 4/19) M
2 | Market Analysis
2.1 | Shortlist 5 Interview Candidates | ALL | 2024-04-15 | 2024-04-16 | 1 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 4 (4/15 - 4/19) T
2.3 | Interview Candidates | ALL | 2024-04-17 | 2024-04-23 | 6 | 0% | bar: WEEK 4 (4/15 - 4/19) M to WEEK 5 (4/22 - 4/26) T
2.4 | Interview Response Analysis | Emily | 2024-04-19 | 2024-04-22 | 3 | 0% | bar: WEEK 4 (4/15 - 4/19) F to WEEK 5 (4/22 - 4/26) M
3 | Prototype Development
3.5 | Midterm Presentation Preparation | Emily/Frenda | 2024-04-29 | 2024-05-10 | 11 | 0% | bar: WEEK 6 (4/29 - 5/3) M to WEEK 7 (5/6 - 5/10) F
3.6 | EDN Notebook Responsibilities | Emily/Frenda | 2024-04-22 | 2024-05-10 | 18 | 0% | bar: WEEK 5 (4/22 - 4/26) M to WEEK 7 (5/6 - 5/10) F
5 | Go-to-Market Stategy
5.1 | Draft Project Report; What More Needs To Be Done? | Frenda/Emily | 2024-05-13 | 2024-05-24 | 11 | 0% | bar: WEEK 8 (5/13 - 5/17) M to WEEK 9 (5/20 - 5/24) F; WEEK 11 6/3 - 6/7) R
5.3 | Final Project Presentation Prep | Emily/Frenda | 2024-05-27 | 2024-06-05 | 8 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R
5.4 | Final Project Presentation | ALL | 2024-05-27 | 2024-06-06 | 9 | 0% | bar: WEEK 10 (5/27 - 5/31) M to WEEK 11 6/3 - 6/7) R